## Sheet1
S.No | Highlevel Steps | Time Needed | Owner
1) | Create VM to install BPA | 2 Days | Mahesh
Create a Repository to store and upload docker images (5 GB)
2) | Create BPA VM | 1 Day | Mahesh
Deploy a linux VM with ARM template
Install Linux VM Agent
Install Azure Pipelines Agent
Install Docker (recommended Version)
3) | Create a Project in ADO | 2 Days | Mahesh
Create a DEV OPS Project
Create a pipeline which deploys a new kubernetes cluster (AKS)
create a pipeline which updates existing kubernets cluster (AKS)
Create a Pipeline which deletes any kubernetes cluster (AKS)
Capture the Endpoints to be configured in BPA
4) | Connect the ADO as adapter to BPA | 1 Day | Mahesh
5) | Create service catalog | 5 Days
| Create a service catalog item. |  | Mahesh
| Create the workflow to call the ADO Endpoint and deploy new AKS Cluster |  | Mahesh
| Update the service Order Action Items. |  | Mahesh & Developer
6) | Upload some Web Application docker image to ADO Repository | 1 Day | Mahesh.
Deploy some Web Application via Service catalog to the AKS cluster
| Total Effort | 12 Days
| Extra Buffer for unforeseen issues | 5 Days